## Slide 1: High level Estimate For Safelite implementation with Instanda policies/coverages
HIGHLY CONFIDENTIAL – DO NOT COPY
10/9/2025

## Slide 2: Option #05: Timelines & Key Activities
Project timeline is based on high level understanding of the current scope
Design,Build & Testing
Planning
Release
Key Activities | Wk-1 9/29 | Wk-2 10/6 | Wk-3 10/13 | Wk-4 10/20 | Wk-5 10/27 | Wk-6 11/03 | Wk-7 11/10 | Wk-8 11/17 | Wk-9 11/24 | Wk-10 12/01 | Wk-11 12/8 | Wk-12 12/15
Scope Identification Evaluating different options for Safelite implementation |  |  |  |  |  |  |  |  |  |  |  | 
Dev and Testing activities Requirements gathering, impact analysis and ETL Design Build and UT Autosys and FTP set up QA/In-Sprint Testing E2E Testing UAT by Project team |  |  |  |  |  |  |  |  |  |  |  | 
Prod Migration KT to BAU team Prod Migration and Warranty Support |  |  |  |  |  |  |  |  |  |  |  | 
Client Support / week (in hrs.) | 2 |  |  |  | 2 |  |  |  | 5 |  |  | 
Key Client Activities | Provide support to onboard the Safelite vendor for testing and signoff Review proposed approach / design solution and provide feedback |  |  |  | Provide the support to clarify any questions, if any Validate UAT test scenarios |  |  |  | Perform UAT testing (data ingestion to DMDM) and provide feedback Provide UAT oversight for Safelite (API testing) & give overall signoff Provide support from AIG Infra team for the production deployment |  |  | 
Sign off for approach for DMDM process
UAT Sign-off
Go Live

## Slide 3: Roles and Responsibilities (current estimate)
Phase | Activities | Deloitte | PCS | AIG | Safelite
Planning & Design | Facilitate engagement with Safelite for the discussions | ✓ |  |  | 
 | Draft, document, and finalize the solution scope, design, and timeline | ✓ |  |  | 
 | Review and approve the design and timelines |  |  | ✓ | 
 | Provision access & approvals to AIG environment for the file transfer and ingestion into DMDM table |  |  | ✓ | 
 | Provision access to Safelite API and relevant jobs |  |  |  | ✓
 | Create test schedule, test cases, and coordinate approvals with Safelite | ✓ |  |  | 
 | Review and approve testing schedule and test cases |  |  | ✓ | ✓
Development | Develop ETL job for the data feed creation & conduct Unit Testing | ✓ |  |  | 
 | Set up folders on PCS SFTP server for the file transfer |  | ✓ |  | 
 | Setup MFT for the file transfer from PCS SFTP location to AIG location |  |  | ✓ | 
 | Develop ETL job for ingestion into AIG DMDM table & conduct Unit Testing | ✓ |  |  | 
 | Conduct reconciliation of data file with control file between PCS and AIG | ✓ |  |  | 
Testing | Coordinate & Manage E2E testing and input, load data for required scenarios into UAT environment | ✓ |  |  | 
 | Conduct UAT testing for data in AIG DMDM table and provide approvals |  |  | ✓ | 
 | Conduct UAT testing for Safelite API results and response validation and provide approvals |  |  |  | ✓
Deployment | Deploy to production (PCS code) |  | ✓ |  | 
 | Deploy to production (AIG code) |  |  | ✓ | 
 | Provide support during the deployment process | ✓ |  |  | 
Hypercare | Warranty Support – 4 weeks | ✓ |  |  | 

## Slide 4: Roles and Responsibilities (E2E estimate)
Phase | Activities | Deloitte | PCS | AIG | Safelite
Planning & Design | Facilitate engagement with Safelite for the discussions | ✓ |  |  | 
 | Draft, document, and finalize the solution scope, design, and timeline | ✓ |  |  | 
 | Review and approve the design and timelines |  |  | ✓ | 
 | Provision access & approvals to AIG environment for the file transfer and ingestion into DMDM table |  |  | ✓ | 
 | Provision access to Safelite API and relevant jobs |  |  |  | ✓
 | Analyze and document Safelite process | ✓ |  |  | 
 | Create test schedule, test cases, and coordinate approvals with Safelite | ✓ |  |  | 
 | Review and approve testing schedule and test cases |  |  | ✓ | ✓
Development | Develop ETL job for the data feed creation & conduct Unit Testing | ✓ |  |  | 
 | Set up folders on PCS SFTP server for the file transfer |  | ✓ |  | 
 | Setup MFT for the file transfer from PCS SFTP location to AIG location |  |  | ✓ | 
 | Develop ETL job for ingestion into AIG DMDM table & conduct Unit Testing | ✓ |  |  | 
 | Conduct reconciliation of data file with control file between PCS and AIG | ✓ |  |  | 
Testing | Coordinate & Manage E2E testing and input, load data for required scenarios into UAT environment | ✓ |  |  | 
 | Conduct UAT testing for data in AIG DMDM table and provide approvals |  |  | ✓ | 
 | Conduct UAT testing for Safelite API results and response validation and provide approvals | ✓ |  |  | ✓
Deployment | Deploy to production (PCS code) |  | ✓ |  | 
 | Deploy to production (AIG code) |  |  | ✓ | 
 | Provide support during the deployment process | ✓ |  |  | 
Hypercare | Warranty Support – 4 weeks | ✓ |  |  | 
Changes Noted in Red

## Slide 5
 | Option #4 Transform monthly to Daily Data Sync-up PCS to AIG | Option #5 New Feed from PCS to AIG and ingest into DMDM coverage table
Pros | No new development of ETL jobs but enhancement of existing 2 sequence jobs to include Instanda data Schedule change from monthly to daily sync-up makes timely accessibility and usability of data for intended business users/downstream systems | No dependency on monthly sync up process and comparatively less maintenance overhead for the newly developed extract/ftp/load jobs Daily data file (Instanda) received from PCS will be loaded into existing DMDM tables without any impact to existing process. Not impacted if monthly sync process is removed or modified in the future
Cons | 80+ tables sync up daily can have maintenance risk, any validation failure can cause delay in entire batch process, impacting timely availability of data for downstream systems Delay in FTP process will cause delay in batch completion (summary tables) and downstream systems Manual updates/deletes by BAU team on the DWH tables needs to be consistent for PCS vs PCG DWH | Delay in FTP process will cause delay in DMDM to Safelite process.
5
We recommend Option 5 as it has no dependencies on the daily PCS to AIG data sync-up, minimizing maintenance requirements and making the solution more future-proof
Option Comparison

## Slide 6: Option- 04: Design
PCS to PCG Daily Sync
Generate files with Control
FTP
PCG DS Landing
Pre validation of Control tables Daily
Daily
Daily
PCG DWH Merge job
Post Validation Daily
PCG DWH to DMDM Safelite load job
Create Autosys job at AIG side to run everyday with dependency on DC or CIP
Modify Autosys schedule from Monthly to Daily at PCS DWH with dependency on INSTANDA
BAU need to monitor validation emails everyday to avoid any failure
Two ETL job change is required to consider INSTANDA SOURCE_SYSTEM_SK
  DMDM_DAILY_SEQ_CIP
  SAFELITE_AU_COV_EDW_TO_DMDM
PCS DWH
PCG DWH

## Slide 7: Option- 05: Design
TPOLICY TVEHICLE TAUTOCOVERAGE
Generate File
FTP
PCG DS Landing
New DataStage DMDM job TSAFELITE_AUTO_COVERAGE
Daily
Daily
Total 6 ETL jobs is to be build, 3 at PCS DWH and 3 at PCG DWH
  Extract job using existing DMDM source query
  Control file script to capture record count
  Sequence job to generate extract and control file
  Load job to update data into TSAFELITE_AUTO_COVERAGE table
  Record count validation script before loading into table
  Sequence job for the orchestration and execution
Autosys job and schedule to run Daily in PCS with dependency on INSTANDA
New MFT job to transfer files from PCS to AIG Daily
PCS DWH
PCG DWH
Daily

## Slide 8: Option- 05: Design
Extract INSTANDA data from TPOLICY TVEHICLE TAUTOCOVERAGE
Generate File
FTP
Daily
Daily
Data is Extracted Daily from TPOLICY, TVEHICLE, TAUTOCOVERAGE in PCS DWH using existing DMDM source query.
Sequence Job to generate extract and control files SAFELITE_$FILEDATE.txt (Data Records File) and SAFELITE_RECORDCOUNT_$FILEDATE.txt (Record Count File).
These Files are the zipped and sent to AIG FTP server using MFT job
Autosys job and schedule to run Daily in PCS with dependency on INSTANDA.
PCS
DWH
Daily

## Slide 9: Option- 05: Design
The zipped data archive is received daily from PCS FTP server and staged at PCG DS landing for processing.
Record count validation script compares:
  The expected record count (from the control file)
  The actual number of records in the data file
If validation fails:
  An automated email notification with expected and actual record counts is sent to the support team.
Load job to update data into TSAFELITE_AUTO_COVERAGE table using upsert mode.
Sequence job orchestrates the validation and data loading steps.
Workflow is scheduled and managed daily using Autosys for automation and reliability.
PCG DWH
FTP
Daily
Daily
Daily
New DataStage DMDM job TSAFELITE_AUTO_COVERAGE
PRE-VALIDATION
Record Count check
PCG DS Landing

## Slide 10: Non-Functional Requirements.
Type | Agreed Approach | Notes
SFTP Location | Yet to be determine | 
No of Files | 1 zipped file | 
File Formats | delimited format, ~ field separate with no quotes | DOS2 Unix conversion may require, placeholder for now 5/2- Tilda ('~') delimited. DOS2 Unix is not required
Code Page settings | UTF-8 | 5/2 Project default is UTF-8. No need to change the framework job.
Header | Header Included | 
Compressed | zip or 7zip | .zip format with GPG encryption
Control/Reconcilation Files | Row Count File | 
Expection Handling | Adhoc Mode incase of any failure | 
Frequency | Daily | 
Timing | Yet to be determine | 
File Name | SAFELITE_$(FILEDATE).txt |