## PCS workstreams
| PCS | AIG
stream1 | Daily Premium Bordereau | Adeptia | Data Curation Services | PR | CRS | GDW | FPSL | SAP-GL
SAP-CD
Surplus Lines
DARs [based on backfeeds]
stream2 | Daily Claims Bordereau | MGA-PCS-Data |  |  | CRS | GDW | FPSL | SAP-GL
DARs [based on backfeeds]
stream3 | Monthly feed [premiums & claims] | PCG-DW |  |  |  | SRM | see pic for downstream flow
|  | Reports |  |  |  | NASH
Jet

## SRM downstream
source: Ashish Mangla

## Impacted Apps
no | gearid | gear name | AIG Technical Lead | time to prepare application using BAU Team | code release required? | QA Testing required? | test cases required? | specific test data needs [if any] | Application QA Team availability | UAT Tester & UAT approver | QA team members
1 | 7270 | Adeptia | Anil Kumar and Alla | 2 weeks | yes | yes | yes | all five products across five states. Clyde to select the states. Test data largely driven by SAP-CD requirements | yes | Anil Kumar and Ian King
2 | 7347 | Data Curation Services | Kvn Babu and Amitava Ghosh | 2 weeks | no | yes | yes | all five products across five states. Clyde to select the states. Test data largely driven by SAP-CD requirements | yes | Anil Kumar and Ian King
3 | 7223 | PCS-MGA-Data | Kvn Babu and Patrick Arulappan | none | no | yes | yes | none | yes - no release therefore no ACAND | Jarome Choi
4 | 1945 | PR | Debbie Schmidt and Veera Reddy | 1 week effort/1 Month elapsed | Yes | Yes | Yes | NA | Yes | Only Tester
5 | 1934 | CRS | Debbie Schmidt and Veera Reddy | 1 week effort/1 Month elapsed | Yes | Yes | Yes | NA | Yes | Only Tester
6 | 2521 | PCG-DW | Kvn Babu & Yakub Shaik | 2 months | yes | yes | yes | TBD | provided by Deloitte | varies - Josmy to manage
7 | 6446 | GDW/Financial Close Data Product | Srilakshmi Potharaboina | none | no | no | no | no | NA | Tracy Terry and Brian Riconda
8 | 7450 | GDW Financial Reporting Product | Krishna Vanka | none | no | regression | no | no | NA | Moku Yashwanth
9 | 6929 / 5700 | FPSL / DCL | Prasad Madhavan/Raj Salaria | 2 weeks | no | yes | no | GDW & SRM outbound files to DCL/FPSL | TBD | Tracy Terry and Brian Riconda
10 | 1524 | SAP-GL | Pareshkumar Jivani/Raj Salaria | 2 weeks | no | yes | no | FPSL | TBD | Tracy Terry and Brian Riconda
11 | 4867 | DARs | Panikumar Nookala | none | no | regression | no | none | NA | Shao, Yi (Kelly)
12 | 1525 | FA-SAP-R3P | Sunil Mantoo/Vinod Vimal | 2 weeks | Yes | Yes | yes | new business, renewals, endorsements, cancel/ reissue and cance/rewrite/Account Current payments | TBD | Jason D Brown' s Team | Reyes, Francis <Francis.Reyes1@aig.com>; Acahen, Maylene <Maylene.Acahen@aig.com>; Muncal, Melvin <Melvin.Muncal@aig.com>
13 | 1604 | FA-SAP-EP3 | Rayna Von Gerard
14 | 6493 | SRM | Thangaraj, Anand | 2 Weeks | No | Yes | No | Monthly Data, Sample policy which is in production and now re-written by MarbleShore | TBD | Fryd Hilary from business and Kaplan Eric from RI IT operations
15 | 1510 | FA-Schedule -F | Achintya Adhikari | 2 Weeks | No | Yes | No | Quarterly data | Yes | Rajasekaran, Ponmurugavel <Ponmurugavel.Rajasekaran@aig.com>; Mayer, Kenneth E <Kenneth.Mayer@aig.com>
16 | 3770 | SL Filing System | Dennis Najar | 8 weeks | yes | yes |  | no |  | Craig Goldman
17 |  | RRD | Maria - update tables? | no testing required

## ASCO
ASCO 40 Marbleshore Speciaty Insurance Co is equal to WWCC 3911
|  | policy # | ASCO | effective date | div
Marbleshore Specialty Insurance Co |  | 123 | Lexington | 2026-03-02 | 72
|  | 123 | Marbleshore | 2027-03-02 | 72
lines:
home
collections
excess liability
excess flood
earthquake
no change to:
DSP Division, section, profit unit | div 72
Major Class [MJC]
change to Marbleshore happens upon renewal OR a new issue

## example - testing timeline
[6 empty] | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5
Workstream | Start | End | owner | Total Work Days | Comments | time axis 2025-11-17 to 2026-01-02
Close Acceleration Test -
CRS > GDW | 2025-12-01 | 2025-12-02 | Veera | 2 | FGEN sends files | bar: 2025-12-01 to 2025-12-02
GDW > FDCL
GDW > FPSL / SRM | 2025-12-03 | 2025-12-04 | Sri | 3 | 5 days to process FGEN data and send to FPSL | bar: 2025-12-03 to 2025-12-04
FPSL > GL / GDW | 2025-12-05 | 2025-12-05 | KC | 1 | 5 days to process and send backfeed to GDW | bar: 2025-12-05
GL [BC4] > GDW [EC1 to BC4 is a critical step for the GL process] | 2025-12-08 | 2025-12-10 | Kriti | 3 | 2 Days to send the GL extract to GDW (backfeed file) | bar: 2025-12-08 to 2025-12-10
SRM [R1 flow - negative test] | 2025-12-10 | 2025-12-10 | Babu | 1 dependent on step8 | 6 days to process data | bar: 2025-12-10
Backfeed load & GDW Datamart Processing | 2025-12-08 | 2025-12-12 | Sri | 7 days dependent on 11 and 12 to start | This is ongoing from the start 9/16 through 10/4 - need to validate | bar: 2025-12-08 to 2025-12-12
GDW dataload for centralized outbound tables | 2025-12-11 | 2025-12-11 | Sri | 1 days dependent on task 11 | bar: 2025-12-11
DARs | 2024-12-15 | 2024-12-18 | Naga/Pani | 4 days dep on task 15 | bar: 2025-12-15 to 2025-12-18
RIPS [RIMS] - combine with reinsurance data | 2024-12-17 | 2024-12-18 | Vadivel | 2
GL - Bus Review | 2024-12-11 | 2024-12-12 | Brian | 2 days dependent on task 12 | bar: 2025-12-11 to 2025-12-12
DARs Bus Review | 2025-12-17 | 2025-12-19 | Kelly | 1 day dependent on task 16 | bar: 2025-12-17 to 2025-12-18
PCG-DW to SRM Test
obtain PCG-DW reinsurance files | 2025-12-11 | 2025-12-11 | Deloitte | 1 | bar: 2025-12-11
PCG-DW to SRM > FPSL / FSCD | 2025-12-15 | 2025-12-15 | Babu | 2 | bar: 2025-12-12; 2025-12-15
SRM > GDW/FPSL/FSCD | 2025-12-15 | 2025-12-15 | Babu | 1 | bar: 2025-12-15
GDW | 2025-12-15 | 2025-12-16 | Sri | dep, 23, 25, 26, 27 | bar: 2025-12-16
FSCD > GL / GDW (SRM data) | 12/XX/2025 | 12/XX/2025 | ??? | 1 | bar: 2025-12-17
FPSL > GL / GDW (SRM data) | 2025-12-18 | 2025-12-18 | KC | 1 | bar: 2025-12-17
GL > GDW (SRM Data) | 2025-12-19 | 2025-12-19 | Kriti | 1 | bar: 2025-12-18
RIPS [RIMS] | 2025-12-30 | 2025-12-30 | Jeevan Kumar | 1 | bar: 2025-12-30
DARs - no testing since this is 'non machine'
SRM Bus Review | 2024-12-22 | 2024-12-23 | Hilary | 1 | bar: 2025-12-22 to 2025-12-23
Note on A6: Ritter, Frances: Financial Data Conformance Layer