## Marbleshore
Addition of Marbleshore UW Company to existing Monthly data sync-up
| Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Curr. Period: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
| ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS (Weeks)
[7 empty] | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  |  | Apr |  |  |  | May |  |  |  | Jun |  |  |  |  | Jul |  |  |  | Aug |  |  |  | Sept |  |  |  |  | Oct |  |  |  | Nov |  |  |  | Dec |  |  |  |  | Jan |  |  |  | Feb
 | time axis 2026-01-05 to 2026-12-28
[59 empty] | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | time axis 2026-01-05 to 2026-12-28
1 | Requirement gathering and impact analysis to understand scope of Tables, Store procedures, Cognos report and Downstream feeds | 10 | 3 |  |  | 50%
2 | Design - To Integrate Marbleshore UW Company to existing Monthly data sync-up process | 12 | 2 |  |  | 40%
3 | Design/approach to exclude sync up for Transactions data, PCS Commission rate & amounts. Apply extra logic to sync up AIG commission rate and amounts | 12 | 1 |  |  | 0%
4 | PCS - ETL Build and UT for Monthly Sync up | 14 | 2 |  |  | 0%
5 | PCG - ETL Build and UT for Monthly Sync up | 14 | 2 |  |  | 0%
6 | PCG Build: One time configuration for addition of Marbleshore UW in reference tables | 14 | 1 |  |  | 0%
7 | PCS In-sprint testing (#4) | 15 | 2 |  |  | 0%
8 | PCG In-sprint testing (#5 , #6) | 15 | 2 |  |  | 0%
9 | Build & UT: Stored Procedure changes (summary tables to include Marbleshore UW) | 14 | 3 |  |  | 0%
10 | PCG In-sprint testing : Store Procedure Changes (#9) | 16 | 3 |  |  | 0%
11 | Cognos Reports - Build and UT | 14 | 4 |  |  | 0%
12 | Cognos Reports - In-sprint testing (#11) | 17 | 3 |  |  | 0%
13 | Downstream feeds ehnacement (SRM & NASH feed) - Build and UT | 14 | 3 |  |  | 0%
14 | SRM & NASH - In Sprint Testing (#13) | 17 | 3 |  |  | 0%
15 | E2E testing : PCS to PCG DW Sync up - Base tables | 20 | 2 |  |  | 0%
16 | E2E testing : Summary tables | 20 | 3 |  |  | 0%
17 | E2E testing : Cognos Reports | 20 | 3 |  |  | 0%
18 | E2E testing - SRM & NASH | 20 | 3 |  |  | 0%
19 | UAT (Cognos Reports & Downstream feeds) | 22 | 3 |  |  | 0%
20 | PROD Migration | 28 | 1 |  |  | 0%
21 | Post Production validations and Operations support | 28 | 4 |  |  | 0%

## Monthly file PCG-DW- 2 LOBS (hidden)
Collections /Yachts - monthly feed to PCG-DW
| Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Curr. Period: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
| ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS (Weeks)
[7 empty] | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  |  | Apr |  |  |  | May |  |  |  | Jun |  |  |  |  | Jul |  |  |  | Aug |  |  |  | Sept |  |  |  |  | Oct |  |  |  | Nov |  |  |  | Dec |  |  |  |  | Jan |  |  |  | Feb
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
1 | Mobilize (DWH inventory scope, Resource on-boarding, Activities plan & timeline) | 9 | 1 |  |  | 100% | bar: Mar 9
2 | PCS Design - Incremental Refresh for Instanda source system data | 10 | 2 |  |  | 80% | bar: Mar 10
3 | PCG Design- Incremental Refresh for Instanda source system data (Merge process at AIG) | 10 | 2 |  |  | 80% | bar: Mar 10
4 | Design/approach to exclude sync up for Transactions data, Third party Commission rate & amounts. Apply extra logic to sync up AIG commission rate and amounts | 10 | 2 |  |  | 40% | bar: Mar 10
5 | PCG Design- Exclude Instanda data for PCG to PCS sync up | 10 | 2 |  |  | 40% | bar: Mar 10
6 | PCS Design- Exclude Instanda data for SDG Claims and DC Installments, Comission Producer | 10 | 2 |  |  | 20% | bar: Mar 10
7 | PCS Build and UT (#2 to #4) | 11 | 4 |  |  | 0%
8 | PCS In-sprint testing (#1 to #4) | 13 | 4 |  |  | 0%
9 | PCG Build and UT (#2 to #4) | 11 | 4 |  |  | 0%
10 | PCG In-sprint testing (#1 to #4) | 13 | 4 |  |  | 0%
11 | PCG Build: One time configuration for policy transaction types | 14 | 1 |  |  | 0%
12 | PCG Build: Analysis and Stored Procedure changes (summary tables to include Instanda data) | 13 | 3 |  |  | 0%
13 | PCG In-sprint testing (#7) | 15 | 2 |  |  | 0%
14 | Cognos Reports - Analysis, Build and UT | 12 | 3 |  |  | 0%
15 | Cognos Reports - In-sprint testing | 15 | 2 |  |  | 0%
16 | Downstream feeds ehnacement (SRM, NASH, SMR, Yacht & Collections In-force files) | 12 | 3 |  |  | 0%
17 | Downstream feeds Testing & Validation (SRM, NASH, SMR, Yacht & Collections In-force files) | 15 | 2 |  |  | 0%
18 | SIT testing | 17 | 3 |  |  | 0%
19 | UAT testing | 19 | 2 |  |  | 0%
20 | Dark mode release/Pre-Prod (if applicable) - Speak with Vinoth | 20 | 1 |  |  | 0%
21 | PROD (Migration and exeuction) | 21 | 1 |  |  | 0%
22 | Post Production validations and Warranty support | 21 | 4 |  |  | 0%
0%
0%
0%
0%
0%
0%

## Assumptions
Assumptions
item | description
1 | PCG to PCS incremental data sync-up approach will be followed for the monthly data sync up between PCS DWH to PCG DWH base tables for the identified Yacht & Collections related tables for Instanda Source system data only.
2 | Assumes the solution of delta records identification process does not require structural changes.
3 | Any new report or modification of reports and building new downstream feeds will be considered a CR.
4 | Assumes End to End testing will be coordinated by program level testing team, data team will be responsible to test only DWH changes .
5 | Required environmental, administrative, and infrastructure support for the upcoming releases will be provided by AIG.

## Option 2 - PCS Data (hidden)
Project Planner
| Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Curr. Period: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
| ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS (Weeks)
[7 empty] | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  |  | Apr |  |  |  | May |  |  |  | Jun |  |  |  |  | Jul |  |  |  | Aug |  |  |  | Sept |  |  |  |  | Oct |  |  |  | Nov |  |  |  | Dec |  |  |  |  | Jan |  |  |  | Feb
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
2 | Data Requirements for Booking & PCG DWH Downstream | 2 | 12 |  |  | 25%
2 | Defne new Landing Format and map to ODS Structures and send data to PCG-DWH | 9 | 8 |  |  | 0%
3 | Map new Data to PR input | 11 | 20 |  |  | 0%
3 | Update Claims Validation to use new BDX Data | 23 | 8 |  |  | 0%
4 | Read new BDX Staging data and map into Existing PCG-DWH Tables | 17 | 18 |  |  | 0%
7 | Re-Insurance Extracts from PCG-DWH for SRM and PCG Jet may need to be enhanced | 29 | 6 |  |  | 0%
8 | Synch-Back of PCG-DWH Data to PCS needs to enhanced to exclude any new BDX Policy Data | 29 | 6 |  |  | 0%
5 | PCS Data Enhance the Home Product TICO Extracts to use new BDX data | 29 | 7 |  |  | 0%
6 | PCS Data has to create the Regulatory Reporting data from the BDX formats for Auto Products | 29 | 12 |  |  | 0%
| Activity 10 |  |  |  |  | 0%
| Activity 11 |  |  |  |  | 0%
| Activity 12 |  |  |  |  | 0%
| Activity 13 |  |  |  |  | 0%
| Activity 14 |  |  |  |  | 0%
| Activity 15 |  |  |  |  | 0%
| Activity 16 |  |  |  |  | 0%
| Activity 17 |  |  |  |  | 0%
| Activity 18 |  |  |  |  | 0%
| Activity 19 |  |  |  |  | 0%
| Activity 20 |  |  |  |  | 0%
| Activity 21 |  |  |  |  | 0%
| Activity 22 |  |  |  |  | 0%
| Activity 23 |  |  |  |  | 0%
| Activity 24 |  |  |  |  | 0%
| Activity 25 |  |  |  |  | 0%
| Activity 26 |  |  |  |  | 0%